## Slide 1: Modeling Orbital Edge Processing in Degraded Communications
Carlo Antonio Nino
09/17/2026
Student Biweekly Progress Presentation to Advisor
1 of 5
Satellite systems increasingly rely on ground communications for processing, routing, and decision support.
This Praxis asks whether bounded orbital edge processing can preserve service and reduce delay when ground-dependent communications are degraded.
A discrete-event simulation compares ground-centric and edge-enabled architectures under identical degradation conditions.
Measures include latency, availability, downtime/recovery, packet loss, and bottleneck delay.
WetLinks, LENS, NOAA/SWPC/NCEI, NASA SCaN, CelesTrak, and international space-weather archives provide public empirical inputs and modeling assumptions.

## Slide 2: Response to Advisor Feedback from previous meeting(s)
2 of 5
Need to think about how to focus the many pieces of this research into something actionable and appropriate. There are lots of moving parts in this research and we need to start consolidating. [06 Sep 2026]
This update defines a bounded DES architecture comparison rather than a broad autonomy study. DES remains the working method.
The current focus is civil communications resilience: uptime, downtime, latency, packet loss, recovery and queueing delay. [16 Sep 2026]
Start utilizing the literature review to narrow down methodology between discrete event simulation and system dynamic simulation. [06 Sep 2026]
Discrete Event Simulation (DES) is the working selection. The literature register supports the choice through queueing, compute-resource, failure, availability and Monte Carlo examples.
System Dynamics remains a previously submitted option, not the active method. [16 Sep 2026] HW 8 and Cal’s Cars. Dr Mazzuchi assignment re-configured.
Need to lock in data sources soon. Make sure all data from external institutions are for public release and available to the public (github, dropbox, etc.). [06 Sep 2026]
Sources are now separated into direct network measurements and environmental inputs.
Germany/WetLinks provides public network files; Canada/LENS clarification is pending. Australia, SANSA, Japan/NICT and NOAA/NCEI support environmental disturbance inputs. Exact file, field, timestamp, reuse and citation checks remain open. [16 Sep 2026]
Notes: Advisor quotations: ResearchReport -- Carlo Nino-Sep 06, 2026.pdf, items 3 and Additional Comments. Red identifies advisor wording, not severity. Yellow: Some Progress remains the normal baseline.
Responses reflect the current user-confirmed direction and artifacts as of 13 September 2026.
FINAL SUBMISSION, SLIDE 2
This Praxis develops a simulation-based systems engineering framework to evaluate autonomous satellite decision support under degraded communications.
The study compares ground-centric routing against an orbital edge-processing path using public orbital data and space-weather indices.
The modeled decisions include onboard filtering, alert prioritization, downlink prioritization, resource allocation, and safe-response recommendations for ground operator review.
The framework evaluates onboard artificial intelligence and machine learning for predictive threat assessment and response.
The model assesses decision latency, operator workload, cognitive burden, and resource utilization through simulation.
The work produces a public-domain feasibility study and a preliminary Concept of Operations.
Validation compares simulated outputs against public benchmarks, theoretical delay calculations, repeated runs, and sensitivity analysis.
The research will not use classified data, develop new algorithms, or build physical hardware.
Scope of Work
SPEAKER NOTES
Modeling Autonomous Satellite Decision-Making in Contested Environments.
can an orbital edge-processing layer provide useful information to the operator faster?
The model focuses on bounded functions such as filtering, prioritizing, routing, allocating resources, and presenting recommendations.
The goal is to measure whether this architecture reduces latency, preserves communications availability, and reduces operator workload using only public, non-CUI data.”
FINAL SUBMISSION, SLIDE 6
(A) Deliverable | | WC
Thesis Statement | This praxis will deliver a simulation-based systems engineering model demonstrating a bounded onboard decision-making framework under degraded communications. | 18
Research Product | Simulation-Based Evaluation Framework | 4
Format | Python/MATLAB/Simulink Model | 3
Deliverable Usage | Systems engineers will use the framework during early architecture trades for onboard processing under degraded communications. | 16
Tie back to PS | The framework will address decision latency by comparing ground-centric routing with bounded onboard decision support under the same scenarios. | 18
New Contributions | This work will contribute a public, repeatable method for evaluating orbital edge-processing performance without classified data or new algorithms. | 18
Scope | The framework will apply to autonomous systems that operate with degraded communications and constrained human oversight. | 16
Main methodology | Discrete-Event Simulation | 3
Inputs | Threat Type (Categorical), Threat Proximity (km), Communication Link Status (Boolean), Satellite Resource Availability (%), AI Confidence Score (%) | NA
Outputs | Response Latency (seconds), Mission Success Probability (%), Resource Consumption (%), Correct Action Taken (Boolean) | NA
Thesis Statement
SPEAKER NOTES
FINAL SUBMISSION, SLIDE 14
Methodology 1
A) Deliverable | B) Content | C) WC
Methodology | Discrete-Event Simulation | 3
Inputs | The Disruption Event Type (categorical), event start times (s), event duration (min), communication lag, ground station availability (Boolean), satellite visibility window (min), bandwidth capacity (Mbps), data volume (MB), packet loss rate (%), edge processing times, AI confidence score (%), satellite resource availability (%) | NA
Outputs | Response latency, OODA Loop decision cycle times, path availability (%), dropped messages (count), recovery time, operator workflow reduction comparison (%), correct action selection (%). | NA
SPEAKER NOTES
Methodology 1 — Discrete-Event Simulation
Method: “My first methodology is discrete-event simulation. It follows specific events in order—such as a request arriving, the ground-station path failing, the edge cloud processing the request, and a response reaching the operator.”
Inputs: “The inputs include the disruption type, when it starts, how long it lasts, communication delay, processing time, and available resources.”
Outputs: “The outputs include response latency, OODA-loop time, path availability, dropped messages, recovery time, workload reduction, and what % of the time the correct response was selected.”
Purpose: “This method shows what happens during each individual disruption and compares the ground-centric path with the edge-enabled path.”

## Slide 3: Progress Since Last Meeting
3 of 5
Updated appendix slides 7–12: civil problem/thesis, refined questions/hypotheses, references, data sources and DES design. [16 Sep 2026]
Literature register: 31 distinct works, all cataloged as GWU D.Eng. Praxes.
Other source types are shown in the five foundational references on slide 10.
Selection criteria: method fit 25 + metric fit 20 + tool/data/V&V fit 15 = 60 of 100 points.
Remaining criteria: domain 20, AIS-layer 10 and transferability 10; scoring retained as recorded. [13 Sep 2026]
GWU CITATION SNAPSHOT — selected methodological examples from the register [16 Sep 2026]
Author / year | Registered work — short title | Method / relevance recorded
Browne (2024) | EV charging: arrivals, utilization and wait times | DES / Monte Carlo; queueing and congestion
Littlefield (2017) | Reliability of highly parallel systems | DES; failures, redundancy and reliability
Shanbhag (2021) | Overcommitment on cloud-computing workloads | DES; finite compute resources and overload
Newell (2023) | Spare-part quantities and obsolescence cycles | DES; failures, repair and operational availability
Devineni (2023) | IT service incident resolution times | DES / Monte Carlo; waiting and resolution time
Data-source progress: WetLinks/Germany and Australia links received; SANSA and NOAA/NCEI clarified environmental-only scope; NICT responded; Canada/LENS remains pending.
Expanded register separates direct-network candidates from environmental-support sources and records contact bounces separately. [16 Sep 2026]
Rubric – Scoring and Grading Criteria
Notes: SOURCE: GWU_Praxis_AIS_Master_Register_2026-09-13_Updated(1).xlsx, Research Library A4:U35 and Scoring Guide. 31 source records; every Institution field says George Washington University. Not a verified completion count and not 31 independent external validations.
Selected citation titles are shortened on the slide; full metadata as recorded follows. No external metadata verification was performed for this deck update.
Dylan Browne (2024). Electric Vehicle Charge Station Expansion Analysis for EV Owners in Maryland: Stochastic Model Utilizing Monte Carlo Simulation Methodology to Determine Arrival Rates, Utilization and Wait Times of Electric Vehicles at Charge Station Infrastructure. GWU D.Eng. Praxis. George Washington University.
https://scholarspace.library.gwu.edu/etd/1v53jx95k
Recorded method: Discrete-event simulation; Monte Carlo; queueing
Recorded role: Potential template for MATLAB/DES experiments on processing queues, link bottlenecks, and latency distributions.
Scott Littlefield (2017). Application of Discrete Event Simulation to Modeling Reliability of Highly Parallel Systems with Common Cause Failures. GWU D.Eng. Praxis. George Washington University.
https://scholarspace.library.gwu.edu/downloads/x059c743t?disposition=inline&locale=en
Recorded method: Discrete-event simulation; reliability; sensitivity analysis
Recorded role: Use for degraded/disrupted architecture scenarios, common-mode failures, redundancy, and sensitivity analysis.
Ravi M. Shanbhag (2021). Implications of Overcommitment on Cloud Computing Workloads. GWU D.Eng. Praxis. George Washington University.
https://scholarspace.library.gwu.edu/concern/gw_etds/bk128b72k
Recorded method: Generative discrete-event simulation; cloud-resource overcommitment
Recorded role: High-value DES precedent for onboard compute queues, utilization limits, congestion, and overload thresholds.
Paul A. Newell Jr. (2023). Reducing System Lifetime Spare Part Quantities Using Obsolescence Cycles: A Discrete Event Simulation. GWU D.Eng. Praxis. George Washington University.
https://search.proquest.com/openview/88a43e1ad35e4f012b3bb98fb476f41b/1?cbl=18750&diss=y&pq-origsite=gscholar
Recorded method: Discrete-event simulation; reliability / repair / inventory / availability modeling
Recorded role: High-value template for availability experiments comparing distributed compute redundancy and degraded ground/space processing.
Kishan Ram Devineni (2023). Improving IT Service Incident Ticket Resolution Times using Lean and Agile Methodologies. GWU D.Eng. Praxis. George Washington University.
https://scholarspace.library.gwu.edu/concern/gw_etds/2j62s577p
Recorded method: Arena discrete-event simulation; Monte Carlo; process redesign
Recorded role: Useful for causal decomposition of end-to-end latency into queues, processing resources, and human workflow effects.

## Slide 4: Issues Encountered and Setbacks
4 of 5
Public links and correspondence are available, but exact file selection, timestamp coverage, field definitions, numerical samples and reuse conditions remain to be completed. [16 Sep 2026] – not automating… where am I going every day to get my data pulls…. Routine….
The service endpoint, outage rule and common units/cadence must be fixed before comparing uptime, downtime, latency and queueing delay.
Queueing observations versus simulated queueing also need to be distinguished. [16 Sep 2026] – normalization.
Environmental records (NOAA/NCEI, ASWFC, SANSA, NICT) are disturbance inputs, not network-performance measurements.
LEO network observations will not be represented as direct measurements of a MEO constellation. [16 Sep 2026]
The final submission contains sample input tables and planned runs.
No completed DES experiment or validation result is reported yet. [16 Sep 2026]
Notes: Open items, not severity escalation. The submitted hypotheses are preserved verbatim on appendix slide 9 and in its notes. Current scope and metric choices come from the user’s September clarification. Evidence status comes from the v05 research-source register.
FINAL SUBMISSION, SLIDE 8
(A) Deliverable | (B) Format | C) WC
Hypothesis 1 | Discrete-event simulation will model autonomous decision latency within 15% of public benchmark ranges. | 13
Independent Variables | AI algorithm processing time (ms), Sensor data ingestion rate (kbps), Number of simulated threats (integer) | NA
Dependent Variable | Modeled response latency (seconds) | NA
Testable | The model's latency output will be compared against latency figures from unclassified literature and theoretical calculations for validation. | 18
Hypothesis 2 | The autonomous framework will reduce response latency by at least 50% compared to a human-in-the-loop baseline. | 16
Independent Variables | Control method (autonomous vs. human-in-the-loop), Communication delay (seconds) | NA
Dependent Variable | Response latency (seconds) | NA
Testable | Run matched scenarios and compare latency distributions using a two-sample K-S test. | 12
Hypothesis 3 | AI confidence score is the most critical parameter affecting the probability of mission success in the autonomous model. | 18
Independent Variables | AI confidence score (%), Satellite resource levels (%), Threat complexity (categorical) | NA
Dependent Variable | Mission success rate (%) | NA
Testable | Conduct a sensitivity analysis by varying each independent variable and measuring the corresponding change in the mission success rate. | 19
Hypothesis
SPEAKER NOTES
FINAL SUBMISSION, SLIDE 16
ID | Name | Source | Brief Description | Format | Time Span | Num. of records | Access
(Y/N)
1 | Orbital Data | Celestrak NORAD GP Element Sets: Current Data | Public orbital elements support satellite visibility and route availability assumptions. | CSV/JSON | Current Scenario snapshot/sample | 30 records | Y
2 | Space Weather | NOAA SWPC Planetary K-Index | Kp values represent geomagnetic/solar storm severity for degraded communications scenarios. | CSV/HTML | Per 30 day window sample period | 240 intervals | Y
3 | Ground Weather | NOAA Local Climate Data | Hourly weather observations support ground-station availability assumptions near a notional antenna for example. | CSV | Per 30 day window sample period | 720 hourly records | Y
4 | C2 Architecture Baseline | NASA SCaN Network Architecture Definition Document, Vol 1, Rev 4 | Architecture descriptions support baseline ground-station and relay network path assumptions. | CSV/PDF | 2013 publication | 1 doc | Y
5 | Resilience Metrics | RAND Resilience Assessment Framework | Resilience framework supporting degraded mission performance comparison. | CSV/PDF | 2023 publication
| 1 doc | Y
6 | Scenario Vectors | Author created MATLAB scenario table | Simulation vectors control outage duration, bandwidth reduction, processing time, and threshold limits. | CSV/MAT | Simulation period | 10,000 runs | Y
Data Sources List
SPEAKER NOTES
Shown up-front, the model does not use classified data, CUI, or internal program data.
The sources either provide public inputs for the simulation or support the assumptions behind the model.
The key point is traceability: every input has a sourced and I updated the earlier slides with the hyperlinks per Instructor feedback.
FINAL SUBMISSION, SLIDE 22
Use controlled simulation inputs to vary degradation, routing, processing, and decision thresholds.
Data treatment:
Generate values from documented distributions and fixed random seeds.
Store each run as a reproducible MATLAB input table
Conduct sensitivity analysis by varying one driver at a time
Scenario Vectors Example
ID | Name | Source | Brief Description | Format | Time Span | Num. of records | Access
(Y/N)
6 | Scenario Vectors | Author created MATLAB scenario table | Simulation vectors control outage duration, bandwidth reduction, processing time, and threshold limits. | CSV/MAT | Simulation period | 10,000 runs | Y
RUN_ID | CONTROL_MODE | COMM_DELAY | RGS_Available | EDGE_PROCESSING | AI_CONFIDENCE_%
1 | Ground-centric | 7.5 | TRUE | 0 | 0
2 | Edge Enabled | 3.2 | FALSE | 0.8 | 82
3 | Edge Enabled | 4.1 | FALSE | 1.1 | 76
Sample Data:
SPEAKER NOTES
Finally, I create a controlled MATLAB scenario table. This combines the public inputs into repeatable events such as an outage, bandwidth reduction, packet loss, processing delay, and recovery.

## Slide 5: Tasks for the Next Two Weeks
5 of 5
Complete a short DES-selection rationale using the registered queueing, compute-resource, failure and availability examples.
Present revised scope, questions and hypotheses for advisor agreement. [Planned; 18 Sep 2026]
Define one common service endpoint, uptime/downtime rule, latency interval and queueing-delay measure for both architectures. Select one bounded initial disruption scenario. [Planned; 24 Sep 2026]
Document benchmark/theory comparison, repeated-run approach, fixed seeds and sensitivity checks; distinguish calibration inputs from validation evidence. [Planned; 25 Sep 2026]
Continue Canada/LENS, Japan/NICT and SANSA/NCEI follow-ups; replace bounced Sri Lanka/Bangladesh contacts if still useful.
Finalize this update for the 17 Sep submission and 19 Sep advising session. [Target 17 Sep 2026]
Notes: Prospective task list, not completed work. Submission target: Thursday 17 September 2026; advising Saturday 19 September 2026. Tasks use the final submission’s documented experimental design and the September 13 source-register state.
FINAL SUBMISSION, SLIDE 14
Methodology 1
A) Deliverable | B) Content | C) WC
Methodology | Discrete-Event Simulation | 3
Inputs | The Disruption Event Type (categorical), event start times (s), event duration (min), communication lag, ground station availability (Boolean), satellite visibility window (min), bandwidth capacity (Mbps), data volume (MB), packet loss rate (%), edge processing times, AI confidence score (%), satellite resource availability (%) | NA
Outputs | Response latency, OODA Loop decision cycle times, path availability (%), dropped messages (count), recovery time, operator workflow reduction comparison (%), correct action selection (%). | NA
SPEAKER NOTES
Methodology 1 — Discrete-Event Simulation
Method: “My first methodology is discrete-event simulation. It follows specific events in order—such as a request arriving, the ground-station path failing, the edge cloud processing the request, and a response reaching the operator.”
Inputs: “The inputs include the disruption type, when it starts, how long it lasts, communication delay, processing time, and available resources.”
Outputs: “The outputs include response latency, OODA-loop time, path availability, dropped messages, recovery time, workload reduction, and what % of the time the correct response was selected.”
Purpose: “This method shows what happens during each individual disruption and compares the ground-centric path with the edge-enabled path.”
FINAL SUBMISSION, SLIDE 16
ID | Name | Source | Brief Description | Format | Time Span | Num. of records | Access
(Y/N)
1 | Orbital Data | Celestrak NORAD GP Element Sets: Current Data | Public orbital elements support satellite visibility and route availability assumptions. | CSV/JSON | Current Scenario snapshot/sample | 30 records | Y
2 | Space Weather | NOAA SWPC Planetary K-Index | Kp values represent geomagnetic/solar storm severity for degraded communications scenarios. | CSV/HTML | Per 30 day window sample period | 240 intervals | Y
3 | Ground Weather | NOAA Local Climate Data | Hourly weather observations support ground-station availability assumptions near a notional antenna for example. | CSV | Per 30 day window sample period | 720 hourly records | Y
4 | C2 Architecture Baseline | NASA SCaN Network Architecture Definition Document, Vol 1, Rev 4 | Architecture descriptions support baseline ground-station and relay network path assumptions. | CSV/PDF | 2013 publication | 1 doc | Y
5 | Resilience Metrics | RAND Resilience Assessment Framework | Resilience framework supporting degraded mission performance comparison. | CSV/PDF | 2023 publication
| 1 doc | Y
6 | Scenario Vectors | Author created MATLAB scenario table | Simulation vectors control outage duration, bandwidth reduction, processing time, and threshold limits. | CSV/MAT | Simulation period | 10,000 runs | Y
Data Sources List
SPEAKER NOTES
Shown up-front, the model does not use classified data, CUI, or internal program data.
The sources either provide public inputs for the simulation or support the assumptions behind the model.
The key point is traceability: every input has a sourced and I updated the earlier slides with the hyperlinks per Instructor feedback.
FINAL SUBMISSION, SLIDE 22
Use controlled simulation inputs to vary degradation, routing, processing, and decision thresholds.
Data treatment:
Generate values from documented distributions and fixed random seeds.
Store each run as a reproducible MATLAB input table
Conduct sensitivity analysis by varying one driver at a time
Scenario Vectors Example
ID | Name | Source | Brief Description | Format | Time Span | Num. of records | Access
(Y/N)
6 | Scenario Vectors | Author created MATLAB scenario table | Simulation vectors control outage duration, bandwidth reduction, processing time, and threshold limits. | CSV/MAT | Simulation period | 10,000 runs | Y
RUN_ID | CONTROL_MODE | COMM_DELAY | RGS_Available | EDGE_PROCESSING | AI_CONFIDENCE_%
1 | Ground-centric | 7.5 | TRUE | 0 | 0
2 | Edge Enabled | 3.2 | FALSE | 0.8 | 82
3 | Edge Enabled | 4.1 | FALSE | 1.1 | 76
Sample Data:
SPEAKER NOTES
Finally, I create a controlled MATLAB scenario table. This combines the public inputs into repeatable events such as an outage, bandwidth reduction, packet loss, processing delay, and recovery.
FINAL SUBMISSION, SLIDE 24
Methodology 1 Map
SPEAKER NOTES
Methodology 1: discrete-event simulation. This method follows individual events in sequence—disruption, routing, edge processing, operator response, and recovery. It helps answer whether the model can credibly measure response latency and path availability during a specific disruption.”

## Slide 6
Appendix

## Slide 7: Problem and Thesis Statements
Problem statement
Ground-dependent satellite data-processing architectures can create decision-support latency, bandwidth bottlenecks and operator workload when communications are degraded or intermittent.
Thesis statement
This Praxis will deliver a simulation-based systems engineering model comparing ground-centric processing with bounded orbital edge processing under degraded communications.
Research product | Intended use / contribution
Simulation-Based Evaluation Framework | Systems engineers will use the framework during early architecture trades for onboard processing under degraded communications.
MATLAB/SimEvents Model | This work contributes a public, repeatable method for evaluating orbital edge-processing performance without classified data, CUI, or new algorithms.
Current working direction: civil ground-centric versus orbital-edge processing under matched degradation using DES, with core measures of uptime/service availability, downtime/recovery, latency, packet loss and queueing delay.
Notes: FINAL SUBMISSION, SLIDE 2
This Praxis develops a simulation-based systems engineering framework to evaluate autonomous satellite decision support under degraded communications.
The study compares ground-centric routing against an orbital edge-processing path using public orbital data and space-weather indices.
The modeled decisions include onboard filtering, alert prioritization, downlink prioritization, resource allocation, and safe-response recommendations for ground operator review.
The framework evaluates onboard artificial intelligence and machine learning for predictive threat assessment and response.
The model assesses decision latency, operator workload, cognitive burden, and resource utilization through simulation.
The work produces a public-domain feasibility study and a preliminary Concept of Operations.
Validation compares simulated outputs against public benchmarks, theoretical delay calculations, repeated runs, and sensitivity analysis.
The research will not use classified data, develop new algorithms, or build physical hardware.
Scope of Work
SPEAKER NOTES
Modeling Autonomous Satellite Decision-Making in Contested Environments.
can an orbital edge-processing layer provide useful information to the operator faster?
The model focuses on bounded functions such as filtering, prioritizing, routing, allocating resources, and presenting recommendations.
The goal is to measure whether this architecture reduces latency, preserves communications availability, and reduces operator workload using only public, non-CUI data.”
FINAL SUBMISSION, SLIDE 5
(A) Deliverable | (B) Format | (C) WC
Issue | Human-in-the-loop satellite control introduces significant latency, which limits timely responses to threats in contested space environments. | 16
Reference | United States Space Force. (2020). Spacepower: Doctrine for Space Forces (CSO-P). https://www.spaceforce.mil/Portals/2/Space%20Capstone%20Publication_10%20Aug%202020.pdf | NA
”so what” | During communication denials, reliance on centralized networks slows the OODA loop, preventing timely target prioritization and jeopardizing mission survival. | 19
Reference | United States Space Force. (2025). Space Warfighting: A Framework for Planners. United States Space Force | NA
Problem statement | The multi-node communication architecture of traditional satellite control creates severe decision latency and operator cognitive burden, slowing the OODA loop and jeopardizing mission survival during communication denials. | 27
Industry | Aerospace and Defense / United States Space Force | NA
PS elaboration 1 | Round-trip data routing from operators to satellites, ground stations, and centralized continental networks creates unsustainable bottlenecks for tactical operations. | 19
PS elaboration 2 | Satellites require edge computing for limited autonomous target acquisition to maintain operational capability when disconnected from the primary network. | 19
Problem Statement
SPEAKER NOTES
FINAL SUBMISSION, SLIDE 6
(A) Deliverable | | WC
Thesis Statement | This praxis will deliver a simulation-based systems engineering model demonstrating a bounded onboard decision-making framework under degraded communications. | 18
Research Product | Simulation-Based Evaluation Framework | 4
Format | Python/MATLAB/Simulink Model | 3
Deliverable Usage | Systems engineers will use the framework during early architecture trades for onboard processing under degraded communications. | 16
Tie back to PS | The framework will address decision latency by comparing ground-centric routing with bounded onboard decision support under the same scenarios. | 18
New Contributions | This work will contribute a public, repeatable method for evaluating orbital edge-processing performance without classified data or new algorithms. | 18
Scope | The framework will apply to autonomous systems that operate with degraded communications and constrained human oversight. | 16
Main methodology | Discrete-Event Simulation | 3
Inputs | Threat Type (Categorical), Threat Proximity (km), Communication Link Status (Boolean), Satellite Resource Availability (%), AI Confidence Score (%) | NA
Outputs | Response Latency (seconds), Mission Success Probability (%), Resource Consumption (%), Correct Action Taken (Boolean) | NA
Thesis Statement
SPEAKER NOTES
The quoted July problem statement retains original terminology. It is not represented as the current civil framing; that refinement is explicitly stated on the slide.

## Slide 8: Research Objectives and Questions
PROPOSED REFINED QUESTIONS — for advisor discussion [16 Sep 2026]
RQ1
Can a discrete-event systems engineering model represent satellite data-processing latency and service availability under degraded communications?
RQ2
Does bounded orbital edge processing reduce end-to-end decision-support latency and preserve service compared with a ground-centric architecture under matched degradation?
RQ3
Which parameters most affect performance: communications delay/loss, bandwidth, outage duration, processing time and alert/data priority?
PURPOSE — current scope
Evaluate bounded orbital edge processing under degraded communications; compare ground-centric routing with an edge-enabled path; provide a repeatable public-data simulation framework for early architecture trades.
Notes: FINAL SUBMISSION, SLIDE 2
This Praxis develops a simulation-based systems engineering framework to evaluate autonomous satellite decision support under degraded communications.
The study compares ground-centric routing against an orbital edge-processing path using public orbital data and space-weather indices.
The modeled decisions include onboard filtering, alert prioritization, downlink prioritization, resource allocation, and safe-response recommendations for ground operator review.
The framework evaluates onboard artificial intelligence and machine learning for predictive threat assessment and response.
The model assesses decision latency, operator workload, cognitive burden, and resource utilization through simulation.
The work produces a public-domain feasibility study and a preliminary Concept of Operations.
Validation compares simulated outputs against public benchmarks, theoretical delay calculations, repeated runs, and sensitivity analysis.
The research will not use classified data, develop new algorithms, or build physical hardware.
Scope of Work
SPEAKER NOTES
Modeling Autonomous Satellite Decision-Making in Contested Environments.
can an orbital edge-processing layer provide useful information to the operator faster?
The model focuses on bounded functions such as filtering, prioritizing, routing, allocating resources, and presenting recommendations.
The goal is to measure whether this architecture reduces latency, preserves communications availability, and reduces operator workload using only public, non-CUI data.”
FINAL SUBMISSION, SLIDE 6
(A) Deliverable | | WC
Thesis Statement | This praxis will deliver a simulation-based systems engineering model demonstrating a bounded onboard decision-making framework under degraded communications. | 18
Research Product | Simulation-Based Evaluation Framework | 4
Format | Python/MATLAB/Simulink Model | 3
Deliverable Usage | Systems engineers will use the framework during early architecture trades for onboard processing under degraded communications. | 16
Tie back to PS | The framework will address decision latency by comparing ground-centric routing with bounded onboard decision support under the same scenarios. | 18
New Contributions | This work will contribute a public, repeatable method for evaluating orbital edge-processing performance without classified data or new algorithms. | 18
Scope | The framework will apply to autonomous systems that operate with degraded communications and constrained human oversight. | 16
Main methodology | Discrete-Event Simulation | 3
Inputs | Threat Type (Categorical), Threat Proximity (km), Communication Link Status (Boolean), Satellite Resource Availability (%), AI Confidence Score (%) | NA
Outputs | Response Latency (seconds), Mission Success Probability (%), Resource Consumption (%), Correct Action Taken (Boolean) | NA
Thesis Statement
SPEAKER NOTES
FINAL SUBMISSION, SLIDE 7
(A) Deliverable | (B) Format | C) WC
Research Question 1 | How effectively can a systems engineering model simulate the performance of an autonomous satellite decision-making architecture? | 16
Research Question 2 | What is the quantifiable reduction in response latency when using an autonomous framework versus a human-in-the-loop model? | 17
Research Question 3 | Which key performance parameters most significantly influence the operational viability of an autonomous satellite in a contested environment? | 18
Research Questions
SPEAKER NOTES
Research questions are reproduced verbatim. The purpose block summarizes the source’s scope/product statements, not an invented set of numbered objectives.

## Slide 9: Research Hypotheses — Proposed Refinement
H0
Under matched degradation, the ground-centric and bounded orbital-edge architectures show no measurable difference in end-to-end latency or service availability.
Test: matched DES runs; compare latency distributions, availability and downtime/recovery using confidence intervals and two-sample K-S tests.
H1
Bounded orbital edge processing reduces end-to-end decision-support latency and improves service availability relative to a ground-centric architecture under degraded communications.
Test: run identical arrival/disruption streams for both architectures; compare mean/P80/P90 latency, uptime/downtime, dropped messages and queueing delay.
H2
The edge-enabled benefit increases during communications degradation or surge conditions.
Test: sensitivity analysis varying outage duration, packet loss, bandwidth, processing time and arrival rate.
For advisor approval: effect-size thresholds and final hypothesis wording remain open. [16 Sep 2026]
Notes: FINAL SUBMISSION, SLIDE 8
(A) Deliverable | (B) Format | C) WC
Hypothesis 1 | Discrete-event simulation will model autonomous decision latency within 15% of public benchmark ranges. | 13
Independent Variables | AI algorithm processing time (ms), Sensor data ingestion rate (kbps), Number of simulated threats (integer) | NA
Dependent Variable | Modeled response latency (seconds) | NA
Testable | The model's latency output will be compared against latency figures from unclassified literature and theoretical calculations for validation. | 18
Hypothesis 2 | The autonomous framework will reduce response latency by at least 50% compared to a human-in-the-loop baseline. | 16
Independent Variables | Control method (autonomous vs. human-in-the-loop), Communication delay (seconds) | NA
Dependent Variable | Response latency (seconds) | NA
Testable | Run matched scenarios and compare latency distributions using a two-sample K-S test. | 12
Hypothesis 3 | AI confidence score is the most critical parameter affecting the probability of mission success in the autonomous model. | 18
Independent Variables | AI confidence score (%), Satellite resource levels (%), Threat complexity (categorical) | NA
Dependent Variable | Mission success rate (%) | NA
Testable | Conduct a sensitivity analysis by varying each independent variable and measuring the corresponding change in the mission success rate. | 19
Hypothesis
SPEAKER NOTES
No null/alternative replacement was created. The slide preserves the original three submitted hypotheses and test descriptions. See current-scope discussion on slide 4.

## Slide 10: 5 Foundational References
EXTERNAL REFERENCE - slides 9–13
Foundational / Domestic Sources | Stated role in the Praxis
Osoba, O. A., Nacouzi, G., Hagen, J., Tran, J., Zhang, L. A., Herron, M., Lynch, C., Eisman, M., & Barton, C. (2023). The resilience assessment framework: Assessing commercial contributions to U.S. Space Force mission resilience (RR-A980-1). RAND Corporation. https://doi.org/10.7249/RRA980-1 https://www.rand.org/content/dam/rand/pubs/research_reports/RRA900/RRA980-1/RAND_RRA980-1.pdf | Resilience assessment and degraded-performance comparison.
National Aeronautics and Space Administration. (2013). Space Communications and Navigation (SCaN) Network Architecture Definition Document (ADD) Executive Summary, Volume 1, Revision 4. NASA. (https://www.nasa.gov/wp-content/uploads/2023/09/scan-add-vol1rev4.pdf) | Ground-station and relay-network architecture; not live performance data.
Kodheli, O., Lagunas, E., Maturo, N., et al. (2021). Satellite communications in the new space era: A survey and future challenges. IEEE Communications Surveys & Tutorials, 23, 70–109. https://ieeexplore.ieee.org/document/9210567 | Satellite communications survey and onboard-processing context.
CelesTrak. (n.d.). NORAD GP element sets: Current data. https://celestrak.org/NORAD/elements/? | Orbital elements for visibility/access assumptions.
National Oceanic and Atmospheric Administration, Space Weather Prediction Center. (n.d.). Planetary K-index. https://www.spaceweather.gov/products/planetary-k-index? | Environmental proxy for degradation scenarios; not direct latency.
Notes: FINAL SUBMISSION, SLIDE 9
(A) Deliverable | (B) Format | (C) WC
Reference | Osoba, O. A., Nacouzi, G., Hagen, J., Tran, J., Zhang, L. A., Herron, M., Lynch, C., Eisman, M., & Barton, C. (2023). The resilience assessment framework: Assessing commercial contributions to U.S. Space Force mission resilience (RR-A980-1). RAND Corporation. https://doi.org/10.7249/RRA980-1
https://www.rand.org/content/dam/rand/pubs/research_reports/RRA900/RRA980-1/RAND_RRA980-1.pdf
| NA
Summary | RAND develops a framework for assessing how architecture changes affect space mission resilience. The framework combines physics-based modeling and statistical systems analysis. | 22
Methodology | Physics-based modeling and statistical systems analysis. | NA
Evaluation | The source is reliable because RAND developed it for USSF mission-resilience assessment.
The limitation is that it evaluates resilience broadly, not orbital edge processing specifically. | 24
Relevance | This source supports architecture-resilience evaluation and degraded-mission performance comparison for my simulation framework.
It helps connect public modeling assumptions to mission-resilience measures without requiring classified data. | 23
Annotated Bibliography
RAND Corp
SPEAKER NOTES
FINAL SUBMISSION, SLIDE 10
(A) Deliverable | (B) Format | (C) WC
Reference | National Aeronautics and Space Administration. (2013). Space Communications and Navigation (SCaN) Network Architecture Definition Document (ADD)
Executive Summary, Volume 1, Revision 4. NASA. (https://www.nasa.gov/wp-content/uploads/2023/09/scan-add-vol1rev4.pdf)
| NA
Summary | NASA describes communications architecture assets, options, and network evolution.
The document links architecture decisions to future mission communications requirements. | 19
Methodology | Architecture definition. | NA
Evaluation | The advantage is that it is civil-space focused, not DoD-specific.
The source is reliable because it is a NASA architecture document. | 21
Relevance | This source supports the ground-station and relay-network portion of my model.
It helps justify modeling communications paths as architecture trade variables. | 22
Annotated Bibliography
NASA SCaN Architecture (Space Communications and Navigation Network )
SPEAKER NOTES
FINAL SUBMISSION, SLIDE 11
(A) Deliverable | (B) Format | (C) WC
Reference | Kodheli, O., Lagunas, E., Maturo, N., et al. (2021). Satellite communications in the new space era: A survey and future challenges. IEEE Communications Surveys & Tutorials, 23, 70–109.
https://ieeexplore.ieee.org/document/9210567
| NA
Summary | The article surveys modern satellite communications and future research challenges.
It identifies onboard processing and space-based data processing as innovation drivers but provides quality standard baselines to measure from. | 21
Methodology | Literature Survey | NA
Evaluation | The source is reliable because it is a highly cited IEEE survey.
The limitation is that it covers many topics beyond my specific model. | 24
Relevance | This source supports onboard processing as a legitimate satellite communications research area.
It helps connect my edge-processing layer to current satellite network research. | 23
Annotated Bibliography
IEEE Communications Surveys
SPEAKER NOTES
FINAL SUBMISSION, SLIDE 12
(A) Deliverable | (B) Format | (C) WC
Reference | CelesTrak. (n.d.). NORAD GP element sets: Current data.
https://celestrak.org/NORAD/elements/?
| NA
Summary | CelesTrak provides public General Perturbations data for orbital modeling.
The data supports repeatable satellite visibility and access assumptions. | 18
Methodology | Public orbital data publication. | NA
Evaluation | The limitation is that public GP data supports notional analysis, not operational precision.
The source is useful because it provides open orbital data. | 23
Relevance | This source provides public orbital context for my MATLAB simulation.
It helps keep the research unclassified, repeatable, and auditable. | 19
Annotated Bibliography
CelesTrak Public Orbital Data
SPEAKER NOTES
FINAL SUBMISSION, SLIDE 13
(A) Deliverable | (B) Format | (C) WC
Reference | National Oceanic and Atmospheric Administration, Space Weather Prediction Center. (n.d.). Planetary K-index.
https://www.spaceweather.gov/products/planetary-k-index?
| NA
Summary | NOAA provides public space-weather products used to characterize geomagnetic disturbances.
Kp helps represent environmental conditions that can affect space and communications systems. | 22
Methodology | Operational environmental observation. | NA
Evaluation | The source is reliable because it is an official NOAA operational product.
The limitation is that Kp is an environmental proxy, not a direct latency measure. | 25
Relevance | This source provides public environmental inputs for simulated degradation scenarios.
It supports unclassified modeling of space-weather effects without using sensitive disruption assumptions.
The proxy is that Kp is an environmental proxy, not a direct man-made measure. | 22
Annotated Bibliography
NOAA Space Weather / Kp Index
SPEAKER NOTES
URLs and author strings are preserved from the final submission. The five entries are a separate snapshot, not added to the 31-work GWU register count.

## Slide 11: Data Sources
INTERNATIONAL DATA SETS — current research-source status
Country / institution / contact | Requested or recorded data role | Evidence / current status
Germany / Netherlands Osnabrück / Twente — N. Aschenbruck | Direct network candidate: RTT, loss, throughput, path/traceroute and weather measurements. | Public repository + dataset/paper links received. Exact files/fields/citation terms still to screen. Shared WetLinks coverage, not a separate Dutch response.
Canada University of Victoria — J. Pan / J. Zhao | Requested direct network data: latency, loss, throughput, interruptions, recovery and path changes. | Clarification supplied to Prof. Pan. Awaiting applicable public LENS files/variables and citation guidance.
Australia ASWFC / Bureau — Cassie Marshall | Environmental support: HF fadeouts, ionospheric observations, regional K-index and flare/Kp referrals. | Archive/API/product links + citation guidance received. Does not establish direct latency/uptime/downtime.
South Africa SANSA — M. Tshisaphungo / K. Niemantinga | Environmental support: geomagnetic/Hermanus data; no direct satellite-link performance data. | Public geomagnetic-data route + research-use terms + preferred citation received. Treat as environmental input.
Japan NICT — Dr. Septi Perwitasari | Environmental support: ionosonde/foF2, TEC and space-weather records; possible communications-data referral. | NICT replied and requested specific products/parameters. Follow-up supplied in Japanese; files pending.
DOMESTIC / INPUTS — previous slide + NCEI follow-up
CelesTrak - orbital elements; NOAA SWPC/NCEI - Kp, GOES-R EXIS XRS/EUVS, GloTEC, ionosonde and event reports; NASA SCaN - architecture; RAND - resilience concepts; scenario vectors - controlled experimental inputs.
Notes: SOURCE: International_Research_Data_POC_Register_2026-09-13_v05_Battle_Rhythm.xlsx, POC Register, Research Fit, Source Status and Australia Sources. The snapshot reports prior correspondence, not newly verified public web content.
Germany: https://github.com/sys-uos ; latest dataset referral https://doi.org/10.26249/FK2/YXPS4G ; associated paper referral https://doi.org/10.1145/3789240.3827586 . Distinguish WetLinks from related/newer datasets when selecting actual files; as-is, no extended support.
Canada: https://onlineacademiccommunity.uvic.ca/starlink/ ; specific files/fields pending.
Australia: Cassie Marshall email of 13 Sep 2026; ASWFC@bom.gov.au. Eight links: https://rudimirz.com/flares/ ; https://listserver.ips.gov.au/pipermail/ips-swf-alert/ ; https://www.sws.bom.gov.au/World_Data_Centre/1/3 ; https://listserver.ips.gov.au/pipermail/ips-mag-alert/ ; https://sws-data.sws.bom.gov.au/ ; https://kp.gfz.de/en/ ; https://listserver.ips.gov.au/pipermail/ips-dsgr/ ; https://www.sws.bom.gov.au/Products_and_Services/4/1 . Bureau material: cite ASWFC/Bureau. X-ray flux: cite original source, not Bureau.
SANSA: targeted RFI sent to mtshisaphungo@sansa.org.za cc spaceweather@sansa.org.za at 15:30 Pacific, 13 Sep 2026.
Japan: iono@ml.nict.go.jp .
FINAL SUBMISSION, SLIDE 16
ID | Name | Source | Brief Description | Format | Time Span | Num. of records | Access
(Y/N)
1 | Orbital Data | Celestrak NORAD GP Element Sets: Current Data | Public orbital elements support satellite visibility and route availability assumptions. | CSV/JSON | Current Scenario snapshot/sample | 30 records | Y
2 | Space Weather | NOAA SWPC Planetary K-Index | Kp values represent geomagnetic/solar storm severity for degraded communications scenarios. | CSV/HTML | Per 30 day window sample period | 240 intervals | Y
3 | Ground Weather | NOAA Local Climate Data | Hourly weather observations support ground-station availability assumptions near a notional antenna for example. | CSV | Per 30 day window sample period | 720 hourly records | Y
4 | C2 Architecture Baseline | NASA SCaN Network Architecture Definition Document, Vol 1, Rev 4 | Architecture descriptions support baseline ground-station and relay network path assumptions. | CSV/PDF | 2013 publication | 1 doc | Y
5 | Resilience Metrics | RAND Resilience Assessment Framework | Resilience framework supporting degraded mission performance comparison. | CSV/PDF | 2023 publication
| 1 doc | Y
6 | Scenario Vectors | Author created MATLAB scenario table | Simulation vectors control outage duration, bandwidth reduction, processing time, and threshold limits. | CSV/MAT | Simulation period | 10,000 runs | Y
Data Sources List
SPEAKER NOTES
Shown up-front, the model does not use classified data, CUI, or internal program data.
The sources either provide public inputs for the simulation or support the assumptions behind the model.
The key point is traceability: every input has a sourced and I updated the earlier slides with the hyperlinks per Instructor feedback.
FINAL SUBMISSION, SLIDE 17
Use public orbital elements to calculate satellite visibility, access windows, and route availability.
Data Treatment:
Select a limited satellite subset aligned to the notional scenario.
Convert all timestamps to UTC for simulation data normalization across the fields.
Filter records with missing or stale orbital elements.
CelesTrak Example
ID | Name | Source | Brief Description | Format | Time Span | Num. of records | Access
(Y/N)
1 | Orbital Data | Celestrak NORAD GP Element Sets: Current Data | Public orbital elements support satellite visibility and route availability assumptions. | CSV/JSON | Current Scenario snapshot/sample | 30 records | Y
Object_Name | NORAD_CAT_ID | EPOCH | INCLINATION | MEAN_MOTION
Sat1 | 001 | UTC Timestamp | degrees | rev/day
Sat2 | 002 | UTC Timestamp | degrees | rev/day
Sat3 | 003 | UTC Timestamp | degrees | rev/day
Sample Data:
SPEAKER NOTES
CelesTrak provides public satellite orbital data. I use it to estimate satellite visibility, access windows, and route availability.
FINAL SUBMISSION, SLIDE 18
Use Kp values to represent space weather degradation severity during simulated communications scenarios.
Data Treatment:
Convert Kp readings into normal, degraded, and severe categories
Align three hour Kp intervals to the simulation clock
Flag missing intervals rather than assuming valid conditions
NOAA Space Weather Prediction Center (SWPC) Kp Example
ID | Name | Source | Brief Description | Format | Time Span | Num. of records | Access
(Y/N)
2 | Space Weather | NOAA SWPC Planetary K-Index | Kp values represent geomagnetic/solar storm severity for degraded communications scenarios. | CSV/HTML | Per 30 day window sample period | 240 intervals | Y
UTC_Time | KP_INDEX | DEGRADATION_LEVEL
7/1/2026 0:00 | 2 | Normal
7/1/2026 3:00 | 5 | Degraded
7/1/2026 6:00 | 7 | Severe
Sample Data:
SPEAKER NOTES
The NOAA Space Weather Prediction Center provides Kp and related space-weather information. I use this to represent environmental conditions that may degrade communications.
FINAL SUBMISSION, SLIDE 19
Use of weather observations to estimate ground station availability representing a notional remote antenna, the Remote Ground Station (RGS).
Data treatment:
Select the nearest public weather station to the notional antenna
Standardize solar, electro-magnetic/polar or gravimetric data
Convert weather values into availability-impact scores.
NOAA National Centers for Environmental Information Weather (NCEI) Example
ID | Name | Source | Brief Description | Format | Time Span | Num. of records | Access
(Y/N)
3 | Ground Weather | NOAA Local Climate Data | Hourly weather observations support ground-station availability assumptions near a notional antenna for example. | CSV | Per 30 day window sample period | 720 hourly records | Y
UTC_TIME | SOURCE | VARIABLE | VALUE | UNIT | DEGRADATION_LEVEL | AVAILABILITY_IMPACT
2026_07_01 00:00 | NOAA NCEI LCD | Visibility | 8 | km | km | Normal
2026_07_01 03:00 | NOAA SWPC Kp | Kp Index | 6 | index | index | Degraded
2026_07_01 04:30 | NOAA GOES X-ray | Radio Blackout | R1 | category | category | Degraded
2026_07_01 06:15 | USGS Earthquake API | Magnitude | 5.6 | Mw | Mw | Severe
Sample Data:
SPEAKER NOTES
The NOAA National Centers for Environmental Information provides historical ground-weather observations near a notional remote ground station.
FINAL SUBMISSION, SLIDE 20
Use public architecture descriptions to define baseline ground station and relay network assumptions.
Data treatment:
Extract architecture elements relevant to the ground, relay and user segments for modeling
Convert qualitative architecture descriptions into notional model states.
Cite derived assumptions rather than treating them as measured data.
NASA SCaN Example
ID | Name | Source | Brief Description | Format | Time Span | Num. of records | Access
(Y/N)
4 | C2 Architecture Baseline | NASA SCaN Network Architecture Definition Document, Vol 1, Rev 4 | Architecture descriptions support baseline ground-station and relay network path assumptions. | CSV/PDF | 2013 publication | 1 doc | Y
ARCHITECTURE_ELEMENT | MODEL_VARIABLE | SIMULATION_ROLE
Ground station | RGS Availability | Baseline path gate
Relay network | Route availability | Alternate path support
User segment | Operator receipt | Decision support endpoint
Sample Data:
SPEAKER NOTES
The NASA SCaN architecture document is not a live dataset. It provides the public architecture baseline for ground stations, relay networks, and communications paths.
FINAL SUBMISSION, SLIDE 21
Use resilience concepts to define degraded mission performance measures and decision criteria.
Data treatment:
Retrieve resilience concepts and ideas relevant to latency, availability, and degradation
Map the concepts and ideas to a measurable simulation output
Use this for methodology support, not direct operational data
RAND Example
ID | Name | Source | Brief Description | Format | Time Span | Num. of records | Access
(Y/N)
5 | Resilience Metrics | RAND Resilience Assessment Framework | Resilience framework supporting degraded mission performance comparison. | CSV/PDF | 2023 publication | 1 doc | Y
RESILIENCE_CONCEPT | MODEL_METRIC | DECISION_CRITERION
Degradation | Path availability (%) | Maintains threshold
Recovery | Recovery time (s) | Restores service
Mission performance | Response latency (s) | Improves baseline
Sample Data:
SPEAKER NOTES
The RAND Resilience Assessment Framework provides resilience concepts and performance measures that help define degradation, recovery, and mission-performance criteria.
FINAL SUBMISSION, SLIDE 22
Use controlled simulation inputs to vary degradation, routing, processing, and decision thresholds.
Data treatment:
Generate values from documented distributions and fixed random seeds.
Store each run as a reproducible MATLAB input table
Conduct sensitivity analysis by varying one driver at a time
Scenario Vectors Example
ID | Name | Source | Brief Description | Format | Time Span | Num. of records | Access
(Y/N)
6 | Scenario Vectors | Author created MATLAB scenario table | Simulation vectors control outage duration, bandwidth reduction, processing time, and threshold limits. | CSV/MAT | Simulation period | 10,000 runs | Y
RUN_ID | CONTROL_MODE | COMM_DELAY | RGS_Available | EDGE_PROCESSING | AI_CONFIDENCE_%
1 | Ground-centric | 7.5 | TRUE | 0 | 0
2 | Edge Enabled | 3.2 | FALSE | 0.8 | 82
3 | Edge Enabled | 4.1 | FALSE | 1.1 | 76
Sample Data:
SPEAKER NOTES
Finally, I create a controlled MATLAB scenario table. This combines the public inputs into repeatable events such as an outage, bandwidth reduction, packet loss, processing delay, and recovery.

## Slide 12: Summary of Methodology
DES — WORKING SELECTION
Element | Working design / source-derived content
Method | Follow individual observations, disruptions, routing, processing, responses and recovery in event order. Compare ground-centric and orbital-edge paths under matched degradation.
Inputs | Disruption type/start/duration; communication lag; ground-station availability; visibility window; bandwidth capacity; data volume; packet loss; edge processing time; resource availability.
Outputs | Uptime/service availability; downtime/recovery; response latency; packet loss; queueing delay. Recovery and dropped messages remain supporting observations. Definitions and thresholds still need to be fixed.
Analysis | Public benchmarks and theoretical delay calculations; matched repeated runs; latency-distribution comparison; sensitivity analysis.
Implementation / boundary | MATLAB/SimEvents primary; Python only optional for data ingestion/preprocessing; reproducible scenario tables with fixed random seeds.
Notes: FINAL SUBMISSION, SLIDE 2
This Praxis develops a simulation-based systems engineering framework to evaluate autonomous satellite decision support under degraded communications.
The study compares ground-centric routing against an orbital edge-processing path using public orbital data and space-weather indices.
The modeled decisions include onboard filtering, alert prioritization, downlink prioritization, resource allocation, and safe-response recommendations for ground operator review.
The framework evaluates onboard artificial intelligence and machine learning for predictive threat assessment and response.
The model assesses decision latency, operator workload, cognitive burden, and resource utilization through simulation.
The work produces a public-domain feasibility study and a preliminary Concept of Operations.
Validation compares simulated outputs against public benchmarks, theoretical delay calculations, repeated runs, and sensitivity analysis.
The research will not use classified data, develop new algorithms, or build physical hardware.
Scope of Work
SPEAKER NOTES
Modeling Autonomous Satellite Decision-Making in Contested Environments.
can an orbital edge-processing layer provide useful information to the operator faster?
The model focuses on bounded functions such as filtering, prioritizing, routing, allocating resources, and presenting recommendations.
The goal is to measure whether this architecture reduces latency, preserves communications availability, and reduces operator workload using only public, non-CUI data.”
FINAL SUBMISSION, SLIDE 6
(A) Deliverable | | WC
Thesis Statement | This praxis will deliver a simulation-based systems engineering model demonstrating a bounded onboard decision-making framework under degraded communications. | 18
Research Product | Simulation-Based Evaluation Framework | 4
Format | Python/MATLAB/Simulink Model | 3
Deliverable Usage | Systems engineers will use the framework during early architecture trades for onboard processing under degraded communications. | 16
Tie back to PS | The framework will address decision latency by comparing ground-centric routing with bounded onboard decision support under the same scenarios. | 18
New Contributions | This work will contribute a public, repeatable method for evaluating orbital edge-processing performance without classified data or new algorithms. | 18
Scope | The framework will apply to autonomous systems that operate with degraded communications and constrained human oversight. | 16
Main methodology | Discrete-Event Simulation | 3
Inputs | Threat Type (Categorical), Threat Proximity (km), Communication Link Status (Boolean), Satellite Resource Availability (%), AI Confidence Score (%) | NA
Outputs | Response Latency (seconds), Mission Success Probability (%), Resource Consumption (%), Correct Action Taken (Boolean) | NA
Thesis Statement
SPEAKER NOTES
FINAL SUBMISSION, SLIDE 14
Methodology 1
A) Deliverable | B) Content | C) WC
Methodology | Discrete-Event Simulation | 3
Inputs | The Disruption Event Type (categorical), event start times (s), event duration (min), communication lag, ground station availability (Boolean), satellite visibility window (min), bandwidth capacity (Mbps), data volume (MB), packet loss rate (%), edge processing times, AI confidence score (%), satellite resource availability (%) | NA
Outputs | Response latency, OODA Loop decision cycle times, path availability (%), dropped messages (count), recovery time, operator workflow reduction comparison (%), correct action selection (%). | NA
SPEAKER NOTES
Methodology 1 — Discrete-Event Simulation
Method: “My first methodology is discrete-event simulation. It follows specific events in order—such as a request arriving, the ground-station path failing, the edge cloud processing the request, and a response reaching the operator.”
Inputs: “The inputs include the disruption type, when it starts, how long it lasts, communication delay, processing time, and available resources.”
Outputs: “The outputs include response latency, OODA-loop time, path availability, dropped messages, recovery time, workload reduction, and what % of the time the correct response was selected.”
Purpose: “This method shows what happens during each individual disruption and compares the ground-centric path with the edge-enabled path.”
FINAL SUBMISSION, SLIDE 15
Methodology 2
A) Deliverable | B) Content | C) WC
Methodology | System Dynamic Simulation | 3
Inputs | Time step(s), simulation duration (hr), path availability (%), bandwidth capacity (Mbps), data volume rate (MB/min), Kp index (0-9), weather severity index (0-1), queue depth (count), edge compute load (%) resource availability (%), AI confidence score (%) | NA
Outputs | Average response latency, 95th percentile latency, OODA loop times, path availability (%), bandwidth demand (Mbps), queue growth rate (messages/min), operator workflow trends (count/hr), resource consumption (%), mission success probability (%).
Dropped messages (count), recovery time, operator workflow reduction comparison, correct action selection (%).
| NA
SPEAKER NOTES
Methodology 2 — System Dynamics Simulation
Method: “My second methodology is system dynamics simulation. It looks at how the entire system behaves and changes over a longer period of time.”
Inputs: “The inputs include simulation time, path availability, incoming data rate, space-weather severity, and available resources.”
Outputs: “The outputs include average latency, 95th-percentile latency, OODA-loop trends, operator workload, resource use, and % mission-success over time.”
Purpose: “This method shows whether the edge-enabled architecture remains effective as degraded conditions continue.
What happens during on-going disruption and compares the ground-centric path with the edge-enabled path.”
Transition: “Methodology 1 shows what happens event by event. Methodology 2 shows how performance changes over time.”
FINAL SUBMISSION, SLIDE 22
Use controlled simulation inputs to vary degradation, routing, processing, and decision thresholds.
Data treatment:
Generate values from documented distributions and fixed random seeds.
Store each run as a reproducible MATLAB input table
Conduct sensitivity analysis by varying one driver at a time
Scenario Vectors Example
ID | Name | Source | Brief Description | Format | Time Span | Num. of records | Access
(Y/N)
6 | Scenario Vectors | Author created MATLAB scenario table | Simulation vectors control outage duration, bandwidth reduction, processing time, and threshold limits. | CSV/MAT | Simulation period | 10,000 runs | Y
RUN_ID | CONTROL_MODE | COMM_DELAY | RGS_Available | EDGE_PROCESSING | AI_CONFIDENCE_%
1 | Ground-centric | 7.5 | TRUE | 0 | 0
2 | Edge Enabled | 3.2 | FALSE | 0.8 | 82
3 | Edge Enabled | 4.1 | FALSE | 1.1 | 76
Sample Data:
SPEAKER NOTES
Finally, I create a controlled MATLAB scenario table. This combines the public inputs into repeatable events such as an outage, bandwidth reduction, packet loss, processing delay, and recovery.
FINAL SUBMISSION, SLIDE 24
Methodology 1 Map
SPEAKER NOTES
Methodology 1: discrete-event simulation. This method follows individual events in sequence—disruption, routing, edge processing, operator response, and recovery. It helps answer whether the model can credibly measure response latency and path availability during a specific disruption.”
Summary combines clearly labeled current scope with inputs and planned analysis in the July source. Complete original DES inputs/outputs, including AI-confidence and operator/action metrics, are retained above as baseline notes; they are not silently asserted as current core measures. No sample figures in the final submission are claimed as downloaded measurements or executed simulation results.

## Slide 15
AIS Cohort Architecture — Company / Technology Register |  |  |  |  |  |  | 
Heat reflects relevance to the Praxis solution space, not vendor quality or endorsement. |  |  |  |  |  |  | 
Layer / Tier | Layer Name | Layer Function | Company | Technology / Descriptor from Slide | Praxis Relevance | Heat | Rationale
5 | Cognitive Layer | Autonomous Software & AI/ML | Advanced Space | SIREN autonomous OODA | Direct AI/ML edge decision-cycle relevance | HOT | Closest fit to autonomous onboard decision support and OODA compression.
5 | Cognitive Layer | Autonomous Software & AI/ML | Force AI | STARHELM secure Rust runtime | Edge software/runtime relevance | HOT | Directly relevant to onboard autonomous software execution.
5 | Cognitive Layer | Autonomous Software & AI/ML | Zenith Space | Cislunar CR3BP normal forms | Autonomy / onboard reasoning adjacency | WARM | Useful autonomy mathematics, but less direct to latency/edge-processing experiments.
5 | Cognitive Layer | Autonomous Software & AI/ML | EraDrive | Era-AI NLP foundation model | AI orchestration / operator support | HOT | Strong human-machine teaming and AI-assisted decision-support relevance.
5 | Cognitive Layer | Autonomous Software & AI/ML | O-Astra ISR | LOGAN pre-approved guard | Autonomous ISR / bounded action logic | HOT | Direct fit to bounded autonomous sensing-to-action concepts.
5 | Cognitive Layer | Autonomous Software & AI/ML | In Orbit Aerospace | INTELLACT zero-hallucination AI | Explainable / reliable onboard AI | HOT | Strong model-credibility and autonomous decision-support relevance.
5 | Cognitive Layer | Autonomous Software & AI/ML | Seekr Technologies | SeekrFlow multi-agent AI | AI orchestration / multi-agent coordination | HOT | Strong fit to autonomous agents and workload triage.
5 | Cognitive Layer | Autonomous Software & AI/ML | PiLogic | Manifest exact CPU-only AI | Compute-constrained edge AI | HOT | Directly relevant to bounded onboard compute and SWaP constraints.
5 | Cognitive Layer | Autonomous Software & AI/ML | Synthetic | SUBSPACE on-orbit reconfigurable ML | On-orbit adaptive ML | HOT | Direct edge-ML and adaptive onboard processing relevance.
4 | Networking Layer | Secure Routing & Timing | Ephemeris Net | SEP optical Layer 3 routing | Optical networking / routing / DDIL | HOT | Direct link to crosslinks, routing, downlink bypass, and communications latency.
4 | Networking Layer | Secure Routing & Timing | Picogrid | MARSO/Legion data middleware | Distributed data middleware | HOT | Relevant to moving and managing data across distributed space nodes.
4 | Networking Layer | Secure Routing & Timing | R-DEX Systems | HSA sub-100ps time fabric | Precision timing / network synchronization | HOT | Timing is foundational to distributed sensing, networking, and latency measurement.
3 | Hardware Layer | SWaP-C High-TOPS Silicon | Starcloud | H100/Blackwell orbit datacenters | Orbital edge/cloud compute | HOT | Near-direct solution-space match for orbital cloud and high-performance edge compute.
3 | Hardware Layer | SWaP-C High-TOPS Silicon | Neuron Dynamics | Compute-in-Memory SSM substrates | Edge compute architecture | HOT | Relevant to constrained onboard processing performance and power.
3 | Hardware Layer | SWaP-C High-TOPS Silicon | Sophia Space | 800 TOPS modular TILEs | High-TOPS modular onboard compute | HOT | Direct hardware precedent for bounded onboard AI/ML processing.
3 | Hardware Layer | SWaP-C High-TOPS Silicon | Web Sensing | SpaceCortex GPU-in-FPGA fabric | Radiation/space compute fabric | HOT | Strong implementation relevance for onboard compute architecture.
3 | Hardware Layer | SWaP-C High-TOPS Silicon | Aethero Space | Radiation-resilient GPUs | Space-qualified GPU compute | HOT | Directly relevant to edge-processing feasibility and resilience.
2 | Perception Layer | Multi-Modal Sensor Payloads | Array Labs | GaN active radar flat tiles | SDA sensing / data-generation source | WARM | Relevant as a high-data-rate sensing source feeding the edge-processing problem.
2 | Perception Layer | Multi-Modal Sensor Payloads | Mithril Tech | Electrostatically-actuated mesh | Sensor/payload architecture adjacency | WARM | Supports perception-layer architecture but is less direct to modeling latency or AI processing.
2 | Perception Layer | Multi-Modal Sensor Payloads | EO Solutions | Passive RF signature fingerprinting | SDA sensing / RF characterization | HOT | Directly relevant to SDA sensing and onboard exploitation opportunities.
2 | Perception Layer | Multi-Modal Sensor Payloads | ThinkOrbital | ThinkX space-to-space X-ray | Novel sensing / high-data payload | WARM | Relevant as a sensor source; useful mainly as a workload/data-volume driver.
2 | Perception Layer | Multi-Modal Sensor Payloads | OWL Integrations | Commodity SDR passive-RF mesh | Distributed RF sensing / networking | HOT | Strong fit to distributed perception, edge processing, and communications-constrained operations.
2 | Perception Layer | Multi-Modal Sensor Payloads | Raptor Dynamix | ARGUS electro-optical & plasma | EO / plasma sensing | WARM | Relevant perception input, but not itself the core edge-processing mechanism.
1 | Platform Layer | High-Maneuver Spacecraft | Orbital Operations | Astraeus LH2/LOX bus + active RBC cooling | Platform / thermal / maneuver support | COLD | Enabling spacecraft layer, but outside the likely core quantitative scope of the Praxis.
1 | Platform Layer | High-Maneuver Spacecraft | Fortastra Corp | Watchdog maneuvering platform (800+ m/s) | Autonomous maneuver / defensive response | WARM | Relevant if the Praxis extends from decision support into bounded action or maneuver response.
1 | Platform Layer | High-Maneuver Spacecraft | Space Kinetic | Whirlwind propellantless payload deployment | Platform / deployment | COLD | Important architecture enabler but relatively distant from edge compute, latency, and AI/ML focus.

## Slide 16
International Research Data Requests — Priority & Mailing Register |  |  |  |  |  |  |  |  |  |  |  |  | 
Purpose: obtain public, scientifically defensible data that parameterize degraded, disrupted, intermittent, or resource-constrained conditions relevant to the Praxis. |  |  |  |  |  |  |  |  |  |  |  |  | 
Primary outreach wave = priorities 1–6. Main bucket = strongest reason to contact; secondary buckets show additional value. |  |  |  |  |  |  |  |  |  |  |  |  | 
Priority | Tier | Country | Entity / Program | Main Data Bucket | Secondary Buckets | Mailing Address | POC / Office | Email | Website / Intake | Status | Date Sent | Response Date | Notes
1 | Tier 1 - Primary | Japan | NICT — World Data Center for Ionosphere & Space Weather | Downlink Bottlenecks & DDIL | Persistent SDA; bounded-response trigger data; workload-event volume | World Data Center for Ionosphere and Space Weather, Space Environment Laboratory, Applied Electromagnetic Research Center, NICT, 4-2-1 Nukui-Kitamachi, Koganei, Tokyo 184-8795, JAPAN | World Data Center for Ionosphere & Space Weather | iono@ml.nict.go.jp | https://wdc.nict.go.jp/wdc-top/contact.html | Responded / clarification | Aug 17; Sep 14 | Sep 14 | NICT requested specific ionosonde/TEC parameters; Japanese follow-up sent. Files pending.
2 | Tier 1 - Primary | Canada | University of Victoria — LENS / Starlink@PanLab | Decision-Cycle Latency | Downlink Bottlenecks & DDIL; response/recovery timing | Department of Computer Science, University of Victoria, Engineering & Computer Science Building, Room 504, PO Box 1700 STN CSC, Victoria, BC V8W 2Y2, CANADA | Jinwei Zhao; Prof. Jianping Pan | clarkzjw@uvic.ca; pan@uvic.ca | https://onlineacademiccommunity.uvic.ca/starlink/ | Responded / awaiting | Aug 17; Sep 13 | Sep 12 | Prof. Pan asked for clarification; LENS latency/loss/uptime variables requested. Files pending.
3 | Tier 1 - Primary | Germany / Netherlands | WetLinks — Osnabrück University / University of Twente | Downlink Bottlenecks & DDIL | Decision-Cycle Latency; environmental correlation | c/o Distributed Systems Group, Institute of Computer Science, Osnabrück University, Friedrich-Janssen-Str. 1, 49076 Osnabrück, GERMANY | Dominic Laniewski; Prof. Nils Aschenbruck; Prof. Roland van Rijswijk-Deij | laniewski@uni-osnabrueck.de; aschenbruck@uni-osnabrueck.de; r.m.vanrijswijk@utwente.nl | https://arxiv.org/abs/2402.16448 | Responded | Aug 17 | Aug 25 | WetLinks public repository + dataset/paper links received; screen files/fields next.
4 | Tier 1 - Primary | Netherlands | RIPE NCC — RIPE Atlas | Decision-Cycle Latency | Downlink Bottlenecks & DDIL; outage/recovery; event-volume inputs | RIPE Network Coordination Centre, P.O. Box 10096, 1001 EB Amsterdam, NETHERLANDS | RIPE Atlas Team | atlas@ripe.net | https://atlas.ripe.net/ | Not Contacted |  |  | Potential independent/original active measurement campaign.
5 | Tier 1 - Primary | New Zealand | University of Otago — Solar Tsunamis / MANA Network | DDIL / Environmental Degradation | Persistent SDA | c/o Department of Physics, University of Otago, PO Box 56, Dunedin 9054, NEW ZEALAND | Dr Johnny Malone-Leigh; Prof. Craig Rodger; Lisa Evans | john.m.leigh@otago.ac.nz; craig.rodger@otago.ac.nz; lisa.evans@otago.ac.nz | https://solartsunamis.otago.ac.nz/mana/mana-data/ | Not Contacted |  |  | Formal scientific data access; Southern Hemisphere geomagnetic disturbance timelines.
6 | Tier 1 - Primary | New Zealand | Earth Sciences New Zealand — Geomagnetism Project | Persistent SDA / Environmental Degradation | DDIL environmental proxy; bounded-response trigger data | Avalon Campus, 1 Fairway Drive, Avalon 5011, PO Box 30-368, Lower Hutt 5040, NEW ZEALAND | Dr Tanja Petersen |  | https://www.gns.cri.nz/about-us/staff-search/tanja-petersen/ | Not Contacted |  |  | INTERMAGNET / Scott Base context; independent validation. General phone: +64 4 570 1444.
7 | Tier 2 - Secondary | Australia | Australian Space Weather Forecasting Centre — Bureau of Meteorology | DDIL / Communications Degradation | Persistent SDA; bounded-response triggers; workload-event volume | Australian Space Weather Forecasting Centre, Bureau of Meteorology, Lot Fourteen, Adelaide, SA 5000, AUSTRALIA | Space Weather Forecaster | ASWFC@bom.gov.au; space@bom.gov.au | https://www.sws.bom.gov.au/Contact_Us | Responded / links | Aug 17; Sep 13 | Sep 13 | ASWFC supplied HF/ionosphere/K-index links + citation guidance; no direct network data.
8 | Tier 2 - Secondary | United Kingdom | Met Office — Space Weather Operations Centre (MOSWOC) | DDIL / Communications Degradation | Persistent SDA; bounded-response triggers; workload-event volume | Met Office, FitzRoy Road, Exeter, Devon EX1 3PB, UNITED KINGDOM | Mark Gibbs / MOSWOC | enquiries@metoffice.gov.uk | https://weather.metoffice.gov.uk/learn-about/space-weather/met-office-role | Not Contacted |  |  | Independent operational flare/radio-blackout/geomagnetic interpretation.
9 | Tier 2 - Secondary | South Africa | SANSA — Space Weather Centre | DDIL / Communications Degradation | Persistent SDA; bounded-response triggers; workload-event volume | SANSA Space Science, PO Box 32, Hermanus 7200, Western Cape, SOUTH AFRICA. Physical site: Hospital Street, Hermanus 7200. | Space Weather Centre / SANSA Space Science | spaceweather@sansa.org.za; spacesci-info@sansa.org.za | https://www.sansa.org.za/products-and-services/space-science/ | Responded / environmental | Aug 17; Sep 13 | Sep 14 | SANSA provided Hermanus geomagnetic-data route/citation; no direct latency/loss/availability.
10 | Tier 2 - Secondary | Belgium | ESA — Space Weather Service Network / Coordination Centre | Persistent SDA / DDIL | Bounded autonomous-response trigger data; workload-event volume | Space Weather Coordination Centre, Space Pole, Avenue Circulaire–Ringlaan 3, 1180 Uccle–Ukkel, BELGIUM | SWE Service Helpdesk | helpdesk.swe@esa.int | https://swe.ssa.esa.int/contact | Not Contacted |  |  | European product-selection, archive, API and V&V support.
11 | Tier 3 - Supporting | Germany | EUMETSAT — User Service | Persistent SDA / Ground-Station Availability | DDIL atmospheric/ground-site proxy | EUMETSAT, Eumetsat-Allee 1, D-64295 Darmstadt, GERMANY | User Service Helpdesk | ops@eumetsat.int | https://www.eumetsat.int/contact-eumetsat | Not Contacted |  |  | Meteorology/precipitation/cloud inputs for notional ground-station availability.
12 | Tier 3 - Supporting | New Zealand | New Zealand Space Agency — MBIE | Cross-Cutting Referral Source | All five families by referral only | New Zealand Space Agency, Ministry of Business, Innovation and Employment, PO Box 1473, Wellington 6140, NEW ZEALAND | New Zealand Space Agency / MBIE | nzspaceagency@mbie.govt.nz | https://www.mbie.govt.nz/science-and-technology/space/connect-with-nzsa | Not Contacted |  |  | Referral/ecosystem source, not primary scientific data.
13 | Tier 3 - Supporting | Germany | ESA Space Debris Office — DISCOS / SDUP | Bounded Autonomous Response / Maneuver Support | Persistent SDA | Space Debris Office, ESOC/ESA, Robert-Bosch-Str. 5, 64293 Darmstadt, GERMANY | Space Debris Office / SDUP Support | space.debris.support@esa.int | https://sdup.esoc.esa.int/contact | Not Contacted |  |  | Public conjunction/object metadata and event-trigger context.
Request framing: seek public, scientifically defensible observations that reproduce system symptoms of degraded/disrupted operations: latency, outages, observation gaps, disturbance onset/recovery, alert volume and quality/confidence. Do not use classified, CUI, proprietary or operational data. |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 17
International Research Data Outreach Register |  |  |  |  |  |  | 
Prioritized POC/data-source register • v07 • 2026-09-16 |  |  |  |  |  |  | 
Metric | Value |  | Priority | Country | Organization | Core Value | Planned wave
Total Targets | 13 |  | 1 | Japan | NICT — World Data Center for Ionosphere & Space Weather | Space weather / ionosphere / solar-flare effects | Wave 1
Tier 1 — Primary | 6 |  | 2 | Canada | University of Victoria — Starlink@PanLab / LENS | LEO latency / one-way delay / network performance | Wave 1
Tier 2 — Secondary | 4 |  | 3 | Germany / Netherlands | WetLinks — Osnabrück University / University of Twente | Starlink RTT / packet loss / throughput / traceroute / weather | Wave 1
Tier 3 — Supporting | 3 |  | 4 | Netherlands | RIPE NCC — RIPE Atlas | Independent active Internet measurements / ping / traceroute | Wave 1
 |  |  | 5 | New Zealand | University of Otago — Solar Tsunamis / MANA Network | Geomagnetic observations / Southern Hemisphere environmental stress | Wave 1
 |  |  | 6 | New Zealand | Earth Sciences New Zealand — Geomagnetism Project | Geomagnetic observatory / INTERMAGNET / Scott Base context | Wave 1
Color | Meaning |  |  |  |  |  | 
Tier 1 | Primary outreach — material value to model/data/V&V |  |  |  |  |  | 
Tier 2 | Secondary wave — cross-validation / operational interpretation |  |  |  |  |  | 
Tier 3 | Supporting — contextual, referral, or lower marginal value |  |  |  |  |  | 
Top table: priority planning. Below: actual six-country postal outreach of August 17. Shared WetLinks coverage is not counted as a separate Dutch reply. |  |  |  |  |  |  | 
FIRST-WAVE RESPONSE STATUS — SEPTEMBER 16, 2026 |  |  |  |  |  |  | 
Packets mailed | 6 | Direct replies | 5 | Auto-reply only | 0 | Archive-link replies | 3
Country | Organization / Contact | Status | Response date | Next action | Data status | Evidence / limits | 
Germany | Osnabrück University - Prof. Dr. Nils Aschenbruck | RESPONDED | Aug 25, 2026 | Inspect/select public files; see shared WetLinks coverage below. | Public links received | GitHub + dataset/paper DOI. Data/code supplied as-is. | 
Canada | University of Victoria - Prof. Jianping Pan | RESPONDED / CLARIFICATION | Sep 12, 2026 | Await LENS file/field guidance after field-specific clarification. | No files yet | Latency/loss/throughput/outage/recovery requested; public variables not confirmed. | 
Japan | NICT - WDC | RESPONDED / CLARIFICATION | Sep 14, 2026 | Await guidance after Japanese follow-up requesting foF2/TEC and network-data referral. | No files yet | NICT asked for product specifics; follow-up supplied with sample period and citation request. | 
Netherlands | University of Twente - shared WetLinks work | Standing by |  | No separate follow-up unless a Twente-specific issue arises. | Shared WetLinks links | Covered by the German reply, per existing register; not an independent Dutch response. | 
South Africa | SANSA - Dr Mpho Tshisaphungo | RESPONDED / ENVIRONMENTAL | Sep 14, 2026 | Use Hermanus geomagnetic data if needed; no direct satellite-link metrics. | Public geomagnetic route | SANSA confirmed public research use/citation; no latency, packet-loss or availability data. | 
Australia | ASWFC / Bureau - Cassie Marshall | RESPONDED / ARCHIVES | Sep 13, 2026 | Inspect archive/API fields and usage terms; clarify regional K-index only if needed. | Public links received | Eight links; citation guidance received. X-ray flux must not be attributed to Bureau. |