## Pitfall_Register
ID | Category | Pitfall/Question | Potential Response/Mitigation | Status
1 | Hardware Constraints | Edge computing requires rad-hardened processors, which have historically lacked the computing power of ground stations. How are the "Edge Run" processing time assumptions realistic? | Acknowledge the historical limitations. Cite recent advancements in rad-tolerant/neuromorphic processors (e.g., from RISC-V, Microchip, BAE Systems) that are closing the performance gap. Frame the model's processing times as projections based on this emerging technology. | Not Started
2 | Model Fidelity | The simulation uses a simplified link model with fixed interruptions and no packet loss. How can the results be considered representative of a complex, contested communication environment? | Acknowledge that this is a Phase 1 model intended to establish a baseline logic. Propose future work to incorporate more complex, trace-driven link models and stochastic packet loss to enhance fidelity. | Not Started
3 | AI/ML Validation | If edge processing relies on AI/ML, how is the model validated? How is the "AI confidence score" generated and what does it represent? What prevents the model from making catastrophic errors? | Specify that the "AI" is bounded and rule-based for this phase. A potential response for future work is to include a robust Verification and Validation (V&V) plan, explainability analysis (e.g., SHAP, LIME), and fault detection/isolation routines. | Not Started
4 | Generalizability | The study uses a limited number of replications and specific random seeds. How can the conclusions be generalized beyond the tested scenarios? | Justify the number of replications for statistical significance in this phase. Propose a broader sensitivity analysis and Monte Carlo runs across a wider range of input distributions in future research to test the robustness of the findings. | Not Started
5 | Cybersecurity | Granting a satellite autonomy to filter data or make decisions creates a new attack surface. How does the architecture defend against cyber threats aimed at compromising the onboard decision logic? | Acknowledge this is out of scope for the current simulation but a critical area for future work. Propose incorporating a threat model (e.g., STRIDE) and simulating the impact of compromised decision logic in a subsequent research phase. | Not Started
6 | Benchmark Validity | The hypothesis aims for latency within 15% of "public benchmarks." Which benchmarks are being used and are they appropriate for validating this specific architecture? | Clearly define the sources for benchmarks (e.g., citing specific IEEE articles, NASA architecture documents, or RAND reports). Justify why the selected benchmarks are the most relevant for a comparative latency analysis of these architectures. | Not Started
7 | Causality / Environmental Data | How do you know a solar or ionospheric event caused the observed communications degradation rather than merely occurring at the same time? | Keep environmental observations and network-performance observations as separate evidence streams. Use environmental data to define disturbance context/scenarios, not to claim causation unless an independently supported mechanism and temporally aligned evidence justify it. | Not Started
8 | Data Fusion | You are combining CAIDA, M-Lab, WetLinks, CINC, NOAA and other sources with different locations, periods, instruments and cadences. What makes those data commensurable? | Define a normalization layer with source, timestamp convention, units, cadence, quality flags, missing-data semantics, station/location and observed-vs-derived status. Fuse only variables with defensible semantic equivalence; otherwise retain them as separate scenario inputs or validation sources. | Not Started
9 | Missing Data | How do you distinguish a missing measurement from an actual outage or non-response event? | Preserve each source's missing-data semantics. Treat absent records, failed probes, explicit non-response, and verified service loss as different states. Never infer outage from missing data alone. | Not Started
10 | Architecture Fairness | Is the bounded-edge architecture being given an unfair advantage by assuming a fixed data-reduction fraction or more favorable processing assumptions? | Use matched arrivals, link states, random seeds and comparable resource assumptions. Model explicit edge-processing costs and sweep the reduction fraction and processing-time parameters in sensitivity analysis so conclusions do not depend on a single favorable assumption. | Not Started
11 | Edge Processing Cost | What penalties are imposed for onboard filtering, including compute time, power, false positives, false negatives, or discarded information? | Include onboard processing time and resource constraints in the DES. Where power or classification error cannot be empirically parameterized, bound them explicitly, test sensitivity, and list them as limitations rather than assuming zero cost. | Not Started
12 | OODA / Cognitive Burden | You claim improved decision support or reduced cognitive burden. What exactly is measured, and how do you avoid overstating a human-factors result that was never experimentally observed? | Use event-to-decision-support latency and workload proxies such as products requiring review, stale products, data volume presented and intervention count. Do not claim measured human cognition unless human-subject evidence exists. Frame OODA relevance as decision-support enablement. | Not Started
13 | Metric Definition | What does service availability mean operationally: link up, packet delivered, product delivered before deadline, or usable decision-support output? | Define service availability before experimentation. Prefer an end-to-end criterion tied to a delivered usable product within a stated threshold, while reporting lower-layer link availability separately. | Not Started
14 | Recovery Definition | When does recovery occur: when the link comes back, when the queue clears, or when service returns below a latency threshold? | Define separate physical/link recovery and functional/service recovery. Measure both, including backlog-clearance time, so restored connectivity is not automatically treated as restored service. | Not Started
15 | Temporal Fidelity | Are empirical time-series structures preserved, or were the data reduced to averages or distributions that destroy burstiness and correlation? | Preserve trace-driven time series where possible. When distributions are used, document what temporal structure is lost and test alternative bursty/correlated scenarios. Avoid replacing all source behavior with long-term averages. | Not Started
16 | Stationarity | Why assume that latency, loss, throughput or outage behavior from one period or location is representative of another? | Do not assume stationarity across geography or time. Treat each dataset as context-specific, stratify by location/period/condition where possible, and use sensitivity analysis to assess transferability. | Not Started
17 | Validation | What independent evidence shows that the DES reproduces real-world behavior rather than merely reflecting its own assumptions? | Validate model outputs against independent public measurements or held-out traces not used for parameterization, plus hand calculations and extreme-condition tests. Document V&V acceptance criteria in advance. | Not Started
18 | Sensitivity / Dominance | If one parameter such as edge data-reduction fraction dominates the result, does the experiment demonstrate an architectural effect or only an input assumption? | Perform one-at-a-time and multi-parameter sensitivity analyses. Identify dominant parameters and report whether the architecture comparison remains directionally consistent across plausible ranges. | Not Started
19 | Operational Thresholds | Why is the service deadline or other performance threshold set at its chosen value, and what source or requirement justifies it? | Tie thresholds to literature, stakeholder/mission requirements, or explicit scenario assumptions. If no authoritative threshold exists, test multiple thresholds and report conclusions as threshold-dependent. | Not Started
20 | Scope Boundary | Why exclude hybrid architectures, optical links, crosslinks, MEO/GEO cases, or other alternatives that could materially change the result? | State that the Praxis intentionally bounds the experiment to a tractable two-architecture comparison. Treat hybrid and alternative-link architectures as future work unless advisor-approved evidence requires inclusion. | Not Started
21 | Public-Data Representativeness | Are public research datasets biased toward nominal or convenient conditions and therefore underrepresent severe disruptions? | Acknowledge selection bias and characterize dataset coverage. Seek disturbed-condition traces where possible, use scenario stress tests for unobserved tails, and avoid claiming representativeness beyond observed conditions. | Not Started
22 | Transferability | How far can Starlink or LEO measurements be transferred to a broader satellite-communications architecture without overgeneralizing? | Use LEO/Starlink data as empirical analogues for selected communications behaviors, not as direct evidence for all orbital regimes. Clearly state the population and architecture represented by each source. | Not Started
23 | Core Claim | Are you demonstrating edge processing, or are you merely demonstrating the assumptions you gave edge processing? | Use matched scenarios, explicit edge costs, empirical parameter ranges and sensitivity analysis. Show that conclusions persist across plausible parameter ranges rather than only at the baseline settings. | Not Started
24 | Primary Endpoint | What is the actual dependent variable when the study reports latency, availability, queueing, recovery, workload proxies and event-to-decision-support timing? | Predeclare a small set of primary endpoints and classify the rest as supporting diagnostics. A defensible structure is primary end-to-end decision-support latency and service availability, with queueing, recovery, loss and workload proxies as explanatory measures. | Not Started